## Sprint Retrospective
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 01-Jul-2026 | 07-Jul-2026 | Harshavi Wagadre | Requirement planning | Unplanned development | Project research | Finalized project requirements and objectives
2 | Sprint 2 | 08-Jul-2026 | 14-Jul-2026 | Harshavi Wagadre | Systematic coding | Frequent unnecessary changes | GitHub updates | Set up FastAPI structure and database
3 | Sprint 3 | 15-Jul-2026 | 21-Jul-2026 | Harshavi Wagadre | Module testing | Manual-only testing | Debugging | Completed Bug Submission Module
4 | Sprint 4 | 22-Jul-2026 | 28-Jul-2026 | Harshavi Wagadre | AI agent integration | Testing everything together | Agent development | Implemented Triage and Log Analysis Agents
5 | Sprint 5 | 29-Jul-2026 | 04-Aug-2026 | Harshavi Wagadre | Historical-data analysis | Ignoring duplicate cases | Knowledge-base improvement | Added historical bug knowledge base and RAG functionality
6 | Sprint 6 | 05-Aug-2026 | 10-Aug-2026 | Harshavi Wagadre | End-to-end testing | Leaving integration issues unresolved | Debugging and testing | Tested multi-agent orchestration and integrated modules
7 | Sprint 7 | 11-Aug-2026 | 16-Aug-2026 | Harshavi Wagadre | Final testing and review | Major last-minute changes | Documentation and presentation | Completed final testing, bug fixes, documentation, and presentation preparation