## Stand up Meeting
SL # | Sprint # | Day | Date | Impediments
1 | Sprint 1 | Day 1 | 2026-07-01 | Project requirements and module responsibilities needed clarification.
|  | Day 2 | 2026-07-02 | Project scope and objectives required further discussion.
|  | Day 3 | 2026-07-03 | Technology stack and system architecture needed finalization.
|  | Day 4 | 2026-07-04 | Functional and non-functional requirements needed review.
|  | Day 5 | 2026-07-05 | Module dependencies and responsibilities required clarification.
|  | Day 6 | 2026-07-06 | Initial project workflow needed refinement.
|  | Day 7 | 2026-07-07 | Final requirement validation was required before development.
2 | Sprint 2 | Day 1 | 2026-07-08 | Initial FastAPI project structure needed setup.
|  | Day 2 | 2026-07-09 | Database models and relationships required review.
|  | Day 3 | 2026-07-10 | FastAPI routes needed validation before integration.
|  | Day 4 | 2026-07-11 | Database connection and configuration required testing.
|  | Day 5 | 2026-07-12 | API request and response schemas needed refinement.
|  | Day 6 | 2026-07-13 | Project structure required cleanup and GitHub synchronization.
|  | Day 7 | 2026-07-14 | Database flow and API integration needed final verification.
3 | Sprint 3 | Day 1 | 2026-07-15 | Bug submission workflow required testing.
|  | Day 2 | 2026-07-16 | Input validation needed improvement.
|  | Day 3 | 2026-07-17 | File upload functionality required support for multiple formats.
|  | Day 4 | 2026-07-18 | Uploaded file content extraction needed validation.
|  | Day 5 | 2026-07-19 | Bug report storage and database operations required testing.
|  | Day 6 | 2026-07-20 | Error handling and invalid input cases needed debugging.
|  | Day 7 | 2026-07-21 | Bug Submission Module required final testing and validation.
4 | Sprint 4 | Day 1 | 2026-07-22 | Triage Agent requirements needed clarification.
|  | Day 2 | 2026-07-23 | Triage Agent classification logic required testing.
|  | Day 3 | 2026-07-24 | Severity and priority prediction needed refinement.
|  | Day 4 | 2026-07-25 | Log Analysis Agent needed stack-trace parsing validation.
|  | Day 5 | 2026-07-26 | Exception extraction required testing with different log formats.
|  | Day 6 | 2026-07-27 | Agent outputs needed a consistent structured format.
|  | Day 7 | 2026-07-28 | Triage and Log Analysis Agents required integration testing.
5 | Sprint 5 | Day 1 | 2026-07-29 | Historical bug dataset required preparation.
|  | Day 2 | 2026-07-30 | Historical bug records needed cleaning and validation.
|  | Day 3 | 2026-07-31 | Knowledge-base structure required refinement.
|  | Day 4 | 2026-08-01 | Relevant historical bugs needed to be retrieved accurately.
|  | Day 5 | 2026-08-02 | Duplicate and similar bug cases required better handling.
|  | Day 6 | 2026-08-03 | RAG retrieval results needed validation and improvement.
|  | Day 7 | 2026-08-04 | Knowledge base and RAG functionality required final testing.
6 | Sprint 6 | Day 1 | 2026-08-05 | Multi-agent orchestration flow needed integration testing.
|  | Day 2 | 2026-08-06 | Agent communication and output combination required debugging.
|  | Day 3 | 2026-08-07 | End-to-end workflow revealed integration issues.
|  | Day 4 | 2026-08-08 | Error handling between modules required improvement.
|  | Day 5 | 2026-08-09 | Database and agent integration needed verification.
|  | Day 6 | 2026-08-10 | Remaining integration issues required debugging before final testing.
7 | Sprint 7 | Day 1 | 2026-08-11 | Final system testing revealed minor bugs requiring fixes.
|  | Day 2 | 2026-08-12 | API responses and user interface required final review.
|  | Day 3 | 2026-08-13 | Documentation required updates based on final implementation.
|  | Day 4 | 2026-08-14 | Presentation content and project explanation needed refinement.
|  | Day 5 | 2026-08-15 | Final bug fixes and testing were required before completion.
|  | Day 6 | 2026-08-16 | Final documentation and presentation preparation required completion.

## Sprint Summary
Sprint | Start Date | End Date | Days | Main Focus | Status
Sprint 1 | 2026-07-01 | 2026-07-14 | 14 | Requirements, project structure, Bug Submission Module | Completed
Sprint 2 | 2026-07-15 | 2026-07-21 | 7 | Triage Agent and Log Analysis Agent | Completed
Sprint 3 | 2026-07-22 | 2026-07-28 | 7 | Multi-Agent Orchestration and structured outputs | Completed
Sprint 4 | 2026-07-29 | 2026-08-04 | 7 | Knowledge Base, RAG retrieval and duplicate detection | Completed
Sprint 5 | 2026-08-05 | 2026-08-11 | 7 | Root Cause and Remediation workflow, integrated testing | Completed
Sprint 6 | 2026-08-12 | 2026-08-13 | 2 | Final testing, Agile documentation and deployment preparation | Completed
Project | Creation of Intelligent Bug Diagnosis Platform with Fix Recommendation Assistance
Team Member | Harshvi Wagadre
Project Timeline | 01-07-2026 to 13-08-2026